## Specification
Order | Requirement | Status | Developed | Tested | Completed | Recommendations | Notes
1 | Create a new document. | Completed | Yes | Yes | Yes
2 | Open existing document. | Completed | Yes | Yes | Yes
3 | Change selected text font Bold, Italic or Underline. | Completed | Yes | Yes | Yes | Use checkbox buttons this increases the functionality of these controls as they can be combined. Selected and deselected. | Unfortunitly I did notice a bug with this approach. The check boxes will also need to be set based on the selected text properties. For example if a word was set to Bold and then the bold button is unchecked. Moving back to the Bold word needs to be set to checked again to reflect the text properties of the selected text or current position of the cursor.
4 | Able to change color of text and background. | Completed | Yes | Yes | Yes
5 | Able to change font and size of text. | Completed | Yes | Yes | Yes
6 | Able to add pre-set words to the document. | Completed | Yes | Yes | Yes | When a new word is entered to the combobox the user needs to press the Enter key to save the word to the library.
7 | Set selected text to Upper and Lower case. | Completed | Yes | Yes | Yes | Recommend to use button controls rather than radio button controls. Buttons are visually more pleasing and constraints when text can be set on selection or all text.
8 | Able to add any of 15 emoticons from panel. | Completed | Yes | Yes | Yes | Include automatic resize of icon based on current text size.
9 | Reset all functions when a new document is selected. | Completed | Yes | Yes | Yes
10 | Save Document | Completed | Yes | Yes | Yes | Ability to save a document. Events have been developed to ask if the user would like to save the document before opening a document, creating a new document or closing the application. | Additional Functionality
11 | View Emoticon or Word Library panals | Completed | Yes | Yes | Yes | Ability to show or hide the Emoticon and Word Library panals based on the View Menu strip selection. | Additional Functionality

## Lookups
status | yesNo
Planning | Yes
Development | No
Completed